# Statement of Work

## Northstar Technologies Professional Services

SOW Number: PS-2023-0147 Customer: Meridian Healthcare Systems Effective Date: July 1, 2023 Project Duration: 12 weeks

## 1. Parties

Service Provider: Northstar Technologies, Inc. 1234 Tech Avenue, Suite 500 Seattle, WA 98101

Customer: Meridian Healthcare Systems 5678 Medical Center Drive Boston, MA 02108

## 2. Project Overview

### 2.1 Background

Meridian Healthcare Systems (“Customer”) has purchased the Northstar Enterprise Platform and requires professional services assistance with implementation, integration, and training. This Statement of Work defines the scope, deliverables, timeline, and fees for these services.

### 2.2 Objectives

- Configure and deploy Northstar Platform for Customer’s environment

- Integrate with Customer’s existing EMR system (Epic)

- Migrate historical data from legacy reporting system

- Train Customer’s staff on platform usage and administration

- Establish HIPAA-compliant data handling procedures

## 3. Scope of Services

### 3.1 In Scope

| Phase | Activities |
| --- | --- |
| Discovery | Requirements gathering, technical assessment, project planning |
| Configuration | Platform setup, user roles, permissions, branding |
| Integration | Epic EMR integration via FHIR API, SSO configuration |
| Data Migration | Legacy data extraction, transformation, validation, loading |
| Testing | UAT support, performance testing, security validation |
| Training | Admin training (2 days), end-user training (3 sessions) |
| Go-Live | Production deployment, hypercare support (2 weeks) |

### 3.2 Out of Scope

The following items are explicitly excluded from this engagement:

- Custom feature development

- Hardware procurement or setup

- Network infrastructure changes

- Third-party software licensing

- Ongoing managed services (separate agreement required)

- Integration with systems other than Epic EMR

- Data migration from sources other than specified legacy system

### 3.3 Assumptions

This SOW is based on the following assumptions:

- Customer will provide timely access to systems, data, and personnel

- Customer’s Epic environment supports FHIR R4 API

- Legacy data is in a supported format (CSV, SQL export)

- Customer has dedicated project manager and technical resources

- Network connectivity between Customer and Northstar environments is available

- HIPAA Business Associate Agreement (BAA) is executed prior to work beginning

## 4. Deliverables

### 4.1 Deliverables List

| ID | Deliverable | Description | Due Date |
| --- | --- | --- | --- |
| D1 | Project Plan | Detailed project plan with milestones | Week 1 |
| D2 | Technical Design | Architecture and integration design document | Week 2 |
| D3 | Configuration Guide | Platform configuration documentation | Week 4 |
| D4 | Integration Specification | Epic FHIR API integration details | Week 4 |
| D5 | Data Migration Report | Data validation and mapping report | Week 6 |
| D6 | Test Plan & Results | UAT test cases and results | Week 8 |
| D7 | Training Materials | Admin and user training documentation | Week 9 |
| D8 | Runbook | Operational procedures document | Week 10 |
| D9 | Go-Live Report | Deployment summary and handoff | Week 12 |

### 4.2 Acceptance Criteria

- All deliverables reviewed and approved by Customer within 5 business days

- Platform passes Customer’s security assessment

- Integration meets documented requirements with < 1% error rate

- Data migration validated with 100% accuracy for critical fields

- Training completion certificates issued to all participants

## 5. Project Schedule

### 5.1 Timeline Overview

Week 1-2:   Discovery & Planning
Week 3-4:   Platform Configuration
Week 5-6:   Integration Development
Week 6-7:   Data Migration
Week 8:     Testing & Validation
Week 9:     Training
Week 10-11: Go-Live Preparation
Week 12:    Go-Live & Hypercare

### 5.2 Key Milestones

| Milestone | Target Date | Acceptance Criteria |
| --- | --- | --- |
| Project Kickoff | July 3, 2023 | Kickoff meeting completed |
| Design Approval | July 14, 2023 | Technical design signed off |
| Integration Complete | August 11, 2023 | API integration tested |
| UAT Complete | August 25, 2023 | All test cases passed |
| Training Complete | September 1, 2023 | All users trained |
| Go-Live | September 15, 2023 | Production deployment |
| Project Close | September 22, 2023 | Final sign-off |

## 6. Project Team

### 6.1 Northstar Resources

| Role | Name | Allocation |
| --- | --- | --- |
| Project Manager | Amanda Thompson | 50% |
| Solutions Architect | Marcus Johnson | 25% |
| Integration Engineer | Jessica Walker | 50% |
| Data Engineer | Priya Sharma | 25% |
| Training Specialist | Kevin Wilson | 25% (Weeks 9-10) |

### 6.2 Customer Resources (Required)

| Role | Responsibilities |
| --- | --- |
| Executive Sponsor | Final decision authority, escalation |
| Project Manager | Day-to-day coordination, scheduling |
| IT Lead | Technical decisions, system access |
| Epic Administrator | EMR integration support |
| Data Steward | Data validation, business rules |
| End User Representatives | UAT participation, training |

## 7. Pricing and Payment

### 7.1 Fixed Fee

| Description | Amount |
| --- | --- |
| Professional Services (as described) | $85,000 |
| Travel & Expenses (estimated) | $8,500 |
| Total | $93,500 |

### 7.2 Payment Schedule

| Milestone | Amount | Due |
| --- | --- | --- |
| Project Kickoff | $28,050 (30%) | Upon execution |
| Design Approval | $28,050 (30%) | Week 2 |
| Go-Live | $28,050 (30%) | Week 12 |
| Project Close | $9,350 (10%) | Upon acceptance |

### 7.3 Additional Services

Services outside the scope of this SOW may be requested and will be provided at the following rates:

| Role | Hourly Rate |
| --- | --- |
| Solutions Architect | $275/hour |
| Integration Engineer | $225/hour |
| Data Engineer | $200/hour |
| Project Manager | $175/hour |
| Training Specialist | $150/hour |

## 8. Change Management

### 8.1 Change Request Process

- Customer submits written change request

- Northstar assesses impact (scope, timeline, cost)

- Northstar provides change order for approval

- Both parties sign change order before work begins

- Project plan updated to reflect approved changes

### 8.2 Change Request Form

Change requests must include: - Description of requested change - Business justification - Desired completion date - Acceptance criteria

## 9. Governance

### 9.1 Communication

| Meeting | Frequency | Participants |
| --- | --- | --- |
| Status Update | Weekly | Project Managers |
| Technical Sync | Bi-weekly | Technical Teams |
| Steering Committee | Bi-weekly | Executive Sponsors |

### 9.2 Reporting

Northstar will provide: - Weekly status report (email) - Risk and issue log (shared document) - Milestone completion notifications

### 9.3 Escalation

| Level | Northstar | Customer |
| --- | --- | --- |
| 1 | Project Manager | Project Manager |
| 2 | Director of PS | IT Director |
| 3 | VP of Customer Success | CIO |

## 10. Terms and Conditions

### 10.1 Warranty

Northstar warrants that services will be performed in a professional manner consistent with industry standards. Any defects in deliverables will be corrected at no additional charge if reported within 30 days of delivery.

### 10.2 Limitation of Liability

Northstar’s total liability under this SOW shall not exceed the total fees paid. Neither party shall be liable for indirect, incidental, or consequential damages.

### 10.3 Confidentiality

Both parties agree to maintain confidentiality of proprietary information disclosed during this engagement. Customer data will be handled in accordance with the executed BAA.

### 10.4 Termination

Either party may terminate this SOW with 30 days written notice. Customer shall pay for all services rendered through the termination date.

## 11. Signatures

This Statement of Work is agreed to by:

Northstar Technologies, Inc.

Signature: _________________________

Name: Lisa Anderson

Title: Director of Customer Success

Date: _________________________

Meridian Healthcare Systems

Signature: _________________________

Name: John Patterson

Title: Chief Information Officer

Date: _________________________

This SOW is governed by the Master Services Agreement between the parties dated January 15, 2022.