## Project Timeline
Project ID | Project Name | Owner | Start Date | End Date | Status | % Complete | Priority | Dependencies | Notes
PRJ-001 | EKS Migration | David Kim | 2023-07-01 | 2023-08-31 | In Progress | 45 | High | None | On track
PRJ-002 | HIPAA Compliance | Ryan Hall | 2023-07-15 | 2023-09-30 | In Progress | 30 | High | PRJ-001 | Audit scheduled
PRJ-003 | Real-time Collaboration | Jessica Walker | 2023-06-01 | 2023-08-15 | In Progress | 75 | High | None | Beta testing
PRJ-004 | Advanced RBAC | Marcus Johnson | 2023-08-01 | 2023-09-15 | Not Started | 0 | Medium | PRJ-002 | Design complete
PRJ-005 | Reporting Engine v2 | Priya Sharma | 2023-08-15 | 2023-10-31 | Not Started | 0 | Medium | PRJ-001 | Requirements gathering
PRJ-006 | Partner Portal | Andrew Robinson | 2023-07-01 | 2023-09-01 | In Progress | 55 | Medium | None | UI review pending
PRJ-007 | Mobile App MVP | Emily Davis | 2023-09-01 | 2023-12-31 | Planning | 5 | Low | PRJ-003 | Q4 priority
PRJ-008 | API v3 Planning | Sarah Chen | 2023-08-01 | 2023-08-31 | In Progress | 20 | Medium | None | RFC in review
PRJ-009 | Data Pipeline Optimization | David Kim | 2023-07-15 | 2023-08-15 | In Progress | 60 | High | None | Cost savings
PRJ-010 | Customer Dashboard Redesign | Emily Davis | 2023-06-15 | 2023-07-31 | Completed | 100 | Medium | None | Shipped in v2.5